## Sheet1
Defect Tracking Tool!
Sr no | Date Reported | List of faults | Description | who was assigned to fix | Date fixed | How was the fault fixed
1 | Nov 8th | button does not work | the new fxml page the new add goal button does not add stuff yet | Alex | Nov 8th | we added the fx id of the button to the fxml as well as added selection for an add goal function
2 | Nov 8th | time period | function that chks that all info is provided for a new date - add chks for timeperiod | Ben | Nov 8th | added logic to only return true only if timeperiod has a selected value along with the preexisting conditions
3 | Nov 8th | change tag | the input bar for goal amt says price | Bolu | Nov 8th | change the tag on the input text
4 | Nov 8th | missing import | missed importing the class goal, hashmap, checkbox | Jowaki | Nov 8th | added the missing imports
5 | Nov 8th | mising semicolen | missing semicolen on a bunch of lines | Carla | Nov 8th | added trhe semicolen
6 | Nov 8th | extra imports | date replaced with local date, propertyvaluefactory not needed in insights controller, goal and transaction classes not needed as already included in user account | Jowaki | Nov 8th | deleted the extra imports
7 | Nov 9th | incorect output in line graph | the sum was not summing and was resetting to zero | Ben | Nov 10th | Resetting the sum to zero at an appropriate location so it would not mess up the output
8 | Nov 9th | round number to 2 decimal places | rounding modes were unecessary | Bolu | Nov 10th | changing the rounding to half even
9 | Nov 9th | names of progress bars were swapped | progress bars were named incorrectly | Bolu | Nov 10th | The names had to be resaiigned to the correct progress bar so the correct data showed up in the correct spot in the UI
10 | Nov 10th | fxid was missing | the id helps id which code coresponds to which button in the controller was missing and so there could be errors | ben | Nov 10th | just included the fx id in the right place
11 | Nov 10th | fix fxid for repeat goal | repeat goal does not have an fxid | jowaki | Nov 10th | adding the fxid to the repeat goad button
12 | Nov 10th | Some missing data | add info under the goal progress bars that we wernt listing b4 | ben | Nov 10th | some data was missing in the code that we initially planed to have on there - so adding new fields and data was the solution
13 | Nov 10th | "==" is miss used | using == to compare strings | everyone - as and when found | N/A | replacing the == with the ".equals()" so the strings were compaired correctly
14 | Nov 10th | flipping between the pages | could not link the 2 pages using the button | ben | Nov 10th | adding a function to bpoth controller classes that was called by the fxml by the button that creates a stage based on the current stage of the application. Used the fxml loader to load the new page and set it to the root of the appliication
15 | Nov 11th | Line graph not working | line graph points not displaying correctly the time period would not sort out correctly when updated | ben | Nov 12th | To fix this the graph had to be cleared and everything to be redrawn again so a new graph would show up.
16 | Nov 12th | bar graph did not work | the function chked if the date is after the section before adding the value to the category which led to the last time period not being calculated at all | ben | Nov 12th | copied the code that uisually ran if the new data is after the current section of time so it runs on the last transaction calculates to make sure all the transactions get added
17 | Nov 12th | bar graph not updating correctly | bargraph function - each new transaction price to the new series so only one transaction was being shown per time period | ben | Nov 12th | instead of adding a new value individually wait till the time period was over - instead initiallised a sum for the timeperiod and then made it zero so the sum was only of the data in the required time period
18
19
20
21
22